## WBS
PROJECT WORK BREAKDOWN STRUCTURE
# | Function/Screen | Feature | Level* | Function/Screen Details | Planned | Status
0 | User Login | Common | Simple | Authentication via JWT, email/password input, error handling | Iteration 1 | Completed
1 | User Register | Common | Simple | Register customer account, OTP verification via email | Iteration 1 | Completed
2 | Reset / Forgot Password | Common | Medium | Send OTP to email, reset password form, validation | Iteration 1 | Completed
3 | User Profile | Common | Simple | View & update user personal info, phone, shipping address | Iteration 1 | Completed
4 | User Management List | Admin | Medium | List all users, filter by role (Admin/FO/CU/Shipper), search | Iteration 1 | Completed
5 | User Detail & Role Assignment | Admin | Complex | Edit user details, assign system roles & RBAC permissions | Iteration 1 | Completed
6 | Room & Floor Management | Admin / Operator | Medium | CRUD cultivation rooms, floors, capacity & room status | Iteration 1 | Completed
7 | Cultivation Tray Management | Admin / Operator | Medium | CRUD trays, link trays to rooms/floors, tray code generation | Iteration 1 | Completed
8 | Mushroom Types Management | Admin | Medium | CRUD mushroom varieties, ideal temp/humidity/CO2 limits | Iteration 2 | Completed
9 | Rental Packages Management | Admin | Simple | CRUD package pricing, duration days, package descriptions | Iteration 2 | Completed
10 | Browse & Rent Packages | Customer | Medium | Package selection, mushroom type choosing, checkout flow | Iteration 2 | Completed
11 | Order & Payment Management | Customer / Admin | Complex | PayOS QR integration, payment link, transaction status tracking | Iteration 2 | Completed
12 | Customer Rented Trays List | Customer | Medium | View active rented trays, cultivation progress percentage, harvest ETA | Iteration 2 | Completed
13 | Real-time Sensor Monitoring | All Roles | Complex | Live graphs for Temp, Humidity, CO2 (5s delay, IoT Telemetry) | Iteration 2 | Completed
14 | IP Camera Stream View | All Roles | Medium | View live camera video feed from cultivation rooms | Iteration 2 | Completed
15 | Master Gateway & RS485 Devices | Admin / Operator | Complex | Manage ESP32-S3 gateways, STM32 sub-nodes, status tracking | Iteration 3 | Completed
16 | SSR Actuator Manual Control | Operator | Medium | Manual toggle for misting, fans, LED lights, heaters (relays) | Iteration 3 | Completed
17 | Automated Control Configuration | Operator / Admin | Complex | Set humidity/temp thresholds, misting pulse ms, cooldown timer | Iteration 3 | Completed
18 | Auto-Control Worker & Runtime Logs | Operator / System | Complex | Background worker execution logs, sensor fault detection | Iteration 3 | In Progress
19 | Cultivation Progress & Stage Tracking | Operator | Medium | Update crop growth stages, progress percent, expected harvest | Iteration 3 | Completed
20 | Harvest Schedule & Yield Recording | Operator | Medium | Record harvest date, actual yield weight, crop quality grade | Iteration 3 | Completed
21 | System Notifications & Alerts | All Roles | Complex | Send threshold alerts, send operator messages, notification modal | Iteration 3 | Completed
22 | Delivery Orders Management | Shipper / Admin | Medium | View assigned deliveries, update shipping status (Picked up/Delivered) | Iteration 3 | In Progress
23 | System Analytics & Reports | Admin | Complex | Export PDF/Excel reports for environment, rental, and harvest stats | Iteration 3 | In Progress
(*) You can rate the functions' complexity based on the number of fields on the screens or the number of transactions in the function, with the details as below
|  | simple | <=7 fields | <=3 transactions
|  | medium | <=15 fields | <= 7 transactions
|  | complex | >15 fields | > 7 transactions
In which:
fields: screen components or database table fields
transactions: action buttons, user or database transactions

## Issues
PROJECT ISSUES
# | Issue | Potential Impact | Priority | Owner | Open Date | Close Date | Status | Notes
1 | RS485 communication noise between ESP32-S3 Gateway and STM32 sub-nodes | Sensor data packet loss (is_valid = false) | High | KhoiLNX | 2026-10-08 | 15/08/2026 | Closed | Added CRC check and 120-ohm termination resistor with TuTA.
2 | PayOS payment webhook delayed response during network spikes | Order status stuck in PENDING payment state | High | KhanhNP | 20/08/2026 | 23/08/2026 | Closed | Implemented polling fallback mechanism in BE API with HuyTTQ.
3 | Camera RTSP stream lag when multi-clients access live view | High memory consumption on backend relay server | Medium | HuyTTQ | 28/08/2026 | 2026-02-09 | Closed | Transcoded stream to HLS with frame-rate throttling.
4 | Auto misting worker trigger overlaps during cooldown periods | Water pump running continuously causing sensor flood | High | KhanhNP | 2026-05-09 | 2026-08-09 | Closed | Enforced strict cooldown_until state locks in PostgreSQL.
5 | Delay in custom PCB fabrication and component delivery | Hardware assembly schedule delayed by 5 days | High | TuTA | 2026-10-09 | 17/09/2026 | Closed | Re-arranged firmware simulation on breadboards first with KhoiLNX.
6 | Notification payload title empty error from API backend | Operator custom messages fail with HTTP 400 | Medium | TongVT | 20/09/2026 | 22/09/2026 | Closed | Updated Web FE modal to strip empty title and send dual-keys.
7 | Shipper delivery location GPS accuracy variance in dense areas | Delays in confirming final mushroom package hand-over | Medium | TuTA | 25/09/2026 |  | Open | Integrated Google Maps Geocoding API on React Mobile App with KhoiLNX.

## Defects
PROJECT DEFECTS
Feature | Function/Screen | Tester | Defect Description | Assign To | Status | Notes
User & Auth | User Register | HuyTTQ | OTP verification timer does not reset after clicking 'Resend OTP' | TuTA | Fixed | Resolved on React Mobile Native client.
Room & Tray | Tray Detail Modal | HuyTTQ | Tray status displays AVAILABLE even after successful rental checkout | KhanhNP | Fixed | Updated DB trigger after payment confirmation.
IoT & Sensor | Real-time Sensor Graph | HuyTTQ | Temperature line chart breaks when receiving null readings | TongVT | Fixed | Added fallback logic on Web Admin UI.
Device Control | Manual SSR Toggle | HuyTTQ | Misting relay switch state in UI does not sync with backend reported state | KhoiLNX | Fixed | Synchronized ESP32-S3 firmware payload reporting with BE.
Auto Control | Threshold Config | HuyTTQ | Minimum humidity allowed to be higher than maximum humidity input | TongVT | Fixed | Added frontend form range validation rules on Web Admin.
Notification | Send Notification Modal | HuyTTQ | Selected notification type always falls back to OPERATOR_MESSAGE | TongVT | Fixed | Sent both type and notification_type payload keys from Web FE.
Harvest | Record Harvest | HuyTTQ | Harvest yield weight accepts negative number input | TongVT | Fixed | Added AntD InputNumber min rule (> 0) on Web Admin.
Delivery | Shipper Orders List | HuyTTQ | Order list fails to refresh after confirming pickup | KhoiLNX | Pending | Fixed state refresh logic on React Mobile App.

## Q&A
PROJECT Q&A
Date | Question | By | Priority | Status | Note (answer, other notes)
2026-05-08 | How should the system handle sensor readings if an STM32 sub-node goes offline? | KhoiLNX | High | Closed | ESP32-S3 marks is_valid = false and sends alert to BE.
2026-12-08 | Should customer be able to rent multiple trays in a single order checkout? | TuTA | High | Closed | Yes, support multiple tray selections per rental package order on React Mobile App.
18/08/2026 | What is the maximum latency allowed for sensor telemetry display on UI? | TongVT | Medium | Closed | Requirement NFR-01 specifies real-time data delay <= 5 seconds.
25/08/2026 | Which payment gateway will be used for tray rental transactions? | KhanhNP | High | Closed | PayOS integration supporting QR code bank transfer payments.
2026-02-09 | How are automated misting cycles controlled per floor? | HuyTTQ | High | Closed | Controlled via iot_auto_control_configs based on target humidity thresholds in BE.
2026-12-09 | Can Farm Operators manually override automated SSR actuators anytime? | TongVT | Medium | Closed | Yes, manual commands sent from Web UI take immediate priority.
22/10/2026 | How should PCB power traces be sized for 8-channel SSR relay switching? | TuTA | High | Closed | Widened high-current AC traces and isolated optocoupler control lines.